## Project Timeline
PROJECT TIMELINE TEMPLATE
TASK NAME | SUB TASK NAME | STATUS | ASSIGNED TO | START DATE | END DATE | DURATION in days | COMMENTS
Documentation | SRS Document & Schedule | Complete | Daniel, Davinder, John, Juan, Skone | 2022-02-15 | 2022-02-21 | 6
Design | Bank Class, ATM Class, Teller Class | In Progress | TBD | 2022-02-22 | 2022-03-27 | 33
Design | Client Class, Manager Class, Officer Class | Not Started | TBD | 2022-02-22 | 2022-03-27 | 33
Bank Class | setBranch(), setTellerID() | Not Started | TBD | 2022-03-28 | 2022-03-31 | 3
Bank Class | setTellerPW(), setAuthLevel(), getBranchID, GetTellerID(), getTellerPW(), getAuthLevel() | Not Started | TBD | 2022-03-28 | 2022-03-31 | 3
Teller Class | deposit(), withdraw() | Not Started | TBD | 2022-04-01 | 2022-04-06 | 5
Teller Class | chkBall(), transfer() | Not Started | TBD | 2022-04-01 | 2022-04-06 | 5
Teller Class | receipt(), login() | Not Started | TBD | 2022-04-01 | 2022-04-06 | 5
Officer Class | newAcct() | Not Started | TBD | 2022-04-07 | 2022-04-10 | 3
Manager Class | isApprove(), viewLedger() | Not Started | TBD | 2022-04-07 | 2022-04-10 | 3
Client Class | setBankID(), setAcctNum() | Not Started | TBD | 2022-04-11 | 2022-04-16 | 5
Client Class | setClientName(), setPin() | Not Started | TBD | 2022-04-11 | 2022-04-16 | 5
Client Class | setBalance(), getBankID(), getAcctNum(), getClientName(), getPin(), getBalance, toString() | Not Started | TBD | 2022-04-11 | 2022-04-16 | 5
ATM Class | isAcct(), isPin() | Not Started | TBD | 2022-04-17 | 2022-04-22 | 5
ATM Class | deposit(), withdraw() | Not Started | TBD | 2022-04-17 | 2022-04-22 | 5
ATM Class | chkBall(), reciept() | Not Started | TBD | 2022-04-17 | 2022-04-22 | 5
Testing |  | Not Started | TBD | 2022-04-23 | 2022-04-28 | 5
Optimzing |  | Not Started | TBD | 2022-04-29 | 2022-05-02 | 3